## API Tasks
TASK ID | LEVEL 0 | LEVEL 1 | LEVEL 2 | METHOD | ENDPOINT | PHASE | PIC | STATUS | NOTE
Sky-Lux-001 | Phase 1 - API Tasks |  |  |  |  | Phase 1
Sky-Lux-002 | Lap trinh Backend API (Core & Auth) | API Authentication (MOD-AUTH) |  |  |  | Phase 1
Sky-Lux-003 |  |  | API-AUTH-001-POST-api-auth-login | POST | /api/auth/login | Phase 1 |  | To Do | Dang nhap
Sky-Lux-004 |  |  | API-AUTH-002-POST-api-auth-logout | POST | /api/auth/logout | Phase 1 |  | To Do | Dang xuat
Sky-Lux-005 |  |  | API-AUTH-003-POST-api-auth-refresh | POST | /api/auth/refresh | Phase 1 |  | To Do | Lam moi token
Sky-Lux-006 |  |  | API-AUTH-004-GET-api-auth-me | GET | /api/auth/me | Phase 1 |  | To Do | Lay thong tin user hien tai
Sky-Lux-007 |  |  | API-AUTH-005-POST-api-auth-change-password | POST | /api/auth/change-password | Phase 1 |  | To Do | Doi mat khau
Sky-Lux-008 | Lap trinh Backend API (Core & Auth) | API Users (MOD-USERS) |  |  |  | Phase 1
Sky-Lux-009 |  |  | API-USERS-001-GET-api-users | GET | /api/users | Phase 1 |  | To Do | Danh sach user
Sky-Lux-010 |  |  | API-USERS-002-GET-api-users-id | GET | /api/users/:id | Phase 1 |  | To Do | Chi tiet user
Sky-Lux-011 |  |  | API-USERS-003-POST-api-users | POST | /api/users | Phase 1 |  | To Do | Tao user
Sky-Lux-012 |  |  | API-USERS-004-PATCH-api-users-id | PATCH | /api/users/:id | Phase 1 |  | To Do | Cap nhat user
Sky-Lux-013 |  |  | API-USERS-005-POST-api-users-id-lock | POST | /api/users/:id/lock | Phase 1 |  | To Do | Khoa user
Sky-Lux-014 |  |  | API-USERS-006-POST-api-users-id-unlock | POST | /api/users/:id/unlock | Phase 1 |  | To Do | Mo khoa user
Sky-Lux-015 |  |  | API-USERS-007-DELETE-api-users-id | DELETE | /api/users/:id | Phase 1 |  | To Do | Xoa user
Sky-Lux-016 | Lap trinh Backend API (Core & Auth) | API Roles / Permissions (MOD-RBAC) |  |  |  | Phase 1
Sky-Lux-017 |  |  | API-RBAC-001-GET-api-roles | GET | /api/roles | Phase 1 |  | To Do | Danh sach role
Sky-Lux-018 |  |  | API-RBAC-002-POST-api-roles | POST | /api/roles | Phase 1 |  | To Do | Tao role
Sky-Lux-019 |  |  | API-RBAC-003-PATCH-api-roles-id | PATCH | /api/roles/:id | Phase 1 |  | To Do | Cap nhat role
Sky-Lux-020 |  |  | API-RBAC-004-GET-api-permissions | GET | /api/permissions | Phase 1 |  | To Do | Danh sach permission
Sky-Lux-021 |  |  | API-RBAC-005-PUT-api-roles-id-permissions | PUT | /api/roles/:id/permissions | Phase 1 |  | To Do | Gan permission cho role
Sky-Lux-022 |  |  | API-RBAC-006-PUT-api-users-id-roles | PUT | /api/users/:id/roles | Phase 1 |  | To Do | Gan role cho user
Sky-Lux-023 | Lap trinh Backend API (Core & Auth) | API Organization / Settings (MOD-ORG) |  |  |  | Phase 1
Sky-Lux-024 |  |  | API-ORG-001-GET-api-organization | GET | /api/organization | Phase 1 |  | To Do | Thong tin organization
Sky-Lux-025 |  |  | API-ORG-002-PATCH-api-organization | PATCH | /api/organization | Phase 1 |  | To Do | Cap nhat organization
Sky-Lux-026 |  |  | API-ORG-003-GET-api-organization-settings | GET | /api/organization/settings | Phase 1 |  | To Do | Danh sach settings
Sky-Lux-027 |  |  | API-ORG-004-PUT-api-organization-settings-key | PUT | /api/organization/settings/:key | Phase 1 |  | To Do | Cap nhat setting theo key
Sky-Lux-028 | Lap trinh Backend API (CRM & Master Data) | API Customers (MOD-CUSTOMER) |  |  |  | Phase 1
Sky-Lux-029 |  |  | API-CUSTOMER-001-GET-api-customers | GET | /api/customers | Phase 1 |  | To Do | Danh sach khach hang
Sky-Lux-030 |  |  | API-CUSTOMER-002-GET-api-customers-id | GET | /api/customers/:id | Phase 1 |  | To Do | Chi tiet khach hang
Sky-Lux-031 |  |  | API-CUSTOMER-003-POST-api-customers | POST | /api/customers | Phase 1 |  | To Do | Tao khach hang
Sky-Lux-032 |  |  | API-CUSTOMER-004-PATCH-api-customers-id | PATCH | /api/customers/:id | Phase 1 |  | To Do | Cap nhat khach hang
Sky-Lux-033 |  |  | API-CUSTOMER-005-DELETE-api-customers-id | DELETE | /api/customers/:id | Phase 1 |  | To Do | Xoa khach hang
Sky-Lux-034 | Lap trinh Backend API (CRM & Master Data) | API Customer Contacts (MOD-CONTACT) |  |  |  | Phase 1
Sky-Lux-035 |  |  | API-CONTACT-001-GET-api-customers-id-contacts | GET | /api/customers/:id/contacts | Phase 1 |  | To Do | Danh sach lien he
Sky-Lux-036 |  |  | API-CONTACT-002-POST-api-customers-id-contacts | POST | /api/customers/:id/contacts | Phase 1 |  | To Do | Tao lien he
Sky-Lux-037 |  |  | API-CONTACT-003-PATCH-api-customers-id-contacts-contactid | PATCH | /api/customers/:id/contacts/:contactId | Phase 1 |  | To Do | Cap nhat lien he
Sky-Lux-038 |  |  | API-CONTACT-004-DELETE-api-customers-id-contacts-contactid | DELETE | /api/customers/:id/contacts/:contactId | Phase 1 |  | To Do | Xoa lien he
Sky-Lux-039 |  |  | API-CONTACT-005-GET-api-customers-id-dossiers | GET | /api/customers/:id/dossiers | Phase 1 |  | To Do | Ho so lien quan den khach hang
Sky-Lux-040 | Lap trinh Backend API (CRM & Master Data) | API Suppliers (MOD-SUPPLIER) |  |  |  | Phase 1
Sky-Lux-041 |  |  | API-SUPPLIER-001-GET-api-suppliers | GET | /api/suppliers | Phase 1 |  | To Do | Danh sach nha cung cap
Sky-Lux-042 |  |  | API-SUPPLIER-002-GET-api-suppliers-id | GET | /api/suppliers/:id | Phase 1 |  | To Do | Chi tiet nha cung cap
Sky-Lux-043 |  |  | API-SUPPLIER-003-POST-api-suppliers | POST | /api/suppliers | Phase 1 |  | To Do | Tao nha cung cap
Sky-Lux-044 |  |  | API-SUPPLIER-004-PATCH-api-suppliers-id | PATCH | /api/suppliers/:id | Phase 1 |  | To Do | Cap nhat nha cung cap
Sky-Lux-045 |  |  | API-SUPPLIER-005-DELETE-api-suppliers-id | DELETE | /api/suppliers/:id | Phase 1 |  | To Do | Xoa nha cung cap
Sky-Lux-046 | Lap trinh Backend API (CRM & Master Data) | API Master Data (MOD-MASTER) |  |  |  | Phase 1
Sky-Lux-047 |  |  | API-MASTER-001-GET-api-master-data-business-lines | GET | /api/master-data/business-lines | Phase 1 |  | To Do | Danh muc mang kinh doanh
Sky-Lux-048 |  |  | API-MASTER-002-GET-api-master-data-market-types | GET | /api/master-data/market-types | Phase 1 |  | To Do | Danh muc loai thi truong
Sky-Lux-049 |  |  | API-MASTER-003-GET-api-master-data-service-categories | GET | /api/master-data/service-categories | Phase 1 |  | To Do | Danh muc nhom dich vu
Sky-Lux-050 |  |  | API-MASTER-004-GET-api-master-data-passenger-types | GET | /api/master-data/passenger-types | Phase 1 |  | To Do | Danh muc loai khach
Sky-Lux-051 |  |  | API-MASTER-005-GET-api-master-data-supplier-types | GET | /api/master-data/supplier-types | Phase 1 |  | To Do | Danh muc loai nha cung cap
Sky-Lux-052 |  |  | API-MASTER-006-GET-api-master-data-units | GET | /api/master-data/units | Phase 1 |  | To Do | Danh muc don vi
Sky-Lux-053 | Lap trinh Backend API (Dossier, Import & Workflow) | API Dossiers (MOD-DOSSIER) |  |  |  | Phase 1
Sky-Lux-054 |  |  | API-DOSSIER-001-GET-api-dossiers | GET | /api/dossiers | Phase 1 |  | To Do | Danh sach ho so
Sky-Lux-055 |  |  | API-DOSSIER-002-GET-api-dossiers-id | GET | /api/dossiers/:id | Phase 1 |  | To Do | Chi tiet ho so
Sky-Lux-056 |  |  | API-DOSSIER-003-PATCH-api-dossiers-id | PATCH | /api/dossiers/:id | Phase 1 |  | To Do | Cap nhat metadata ho so
Sky-Lux-057 | Lap trinh Backend API (Dossier, Import & Workflow) | API Import Excel (MOD-IMPORT) |  |  |  | Phase 1
Sky-Lux-058 |  |  | API-IMPORT-001-POST-api-imports | POST | /api/imports | Phase 1 |  | To Do | Upload file import
Sky-Lux-059 |  |  | API-IMPORT-002-GET-api-imports-id | GET | /api/imports/:id | Phase 1 |  | To Do | Trang thai import
Sky-Lux-060 |  |  | API-IMPORT-003-GET-api-imports-id-preview | GET | /api/imports/:id/preview | Phase 1 |  | To Do | Preview du lieu import
Sky-Lux-061 |  |  | API-IMPORT-004-GET-api-imports-id-errors | GET | /api/imports/:id/errors | Phase 1 |  | To Do | Danh sach loi import
Sky-Lux-062 |  |  | API-IMPORT-005-PATCH-api-imports-id-rows-rowid | PATCH | /api/imports/:id/rows/:rowId | Phase 1 |  | To Do | Sua row staging
Sky-Lux-063 |  |  | API-IMPORT-006-POST-api-imports-id-validate | POST | /api/imports/:id/validate | Phase 1 |  | To Do | Validate lai import
Sky-Lux-064 |  |  | API-IMPORT-007-POST-api-imports-id-confirm | POST | /api/imports/:id/confirm | Phase 1 |  | To Do | Confirm import thanh ho so
Sky-Lux-065 | Lap trinh Backend API (Dossier, Import & Workflow) | API Estimates (MOD-ESTIMATE) |  |  |  | Phase 1
Sky-Lux-066 |  |  | API-ESTIMATE-001-GET-api-dossiers-id-estimates | GET | /api/dossiers/:id/estimates | Phase 1 |  | To Do | Danh sach estimate cua ho so
Sky-Lux-067 |  |  | API-ESTIMATE-002-GET-api-estimates-id | GET | /api/estimates/:id | Phase 1 |  | To Do | Chi tiet estimate
Sky-Lux-068 |  |  | API-ESTIMATE-003-PATCH-api-estimates-id | PATCH | /api/estimates/:id | Phase 1 |  | To Do | Cap nhat estimate
Sky-Lux-069 | Lap trinh Backend API (Dossier, Import & Workflow) | API Workflow / Approvals (MOD-WORKFLOW) |  |  |  | Phase 1
Sky-Lux-070 |  |  | API-WORKFLOW-001-POST-api-dossiers-id-submit | POST | /api/dossiers/:id/submit | Phase 1 |  | To Do | Submit ho so
Sky-Lux-071 |  |  | API-WORKFLOW-002-POST-api-dossiers-id-start-review | POST | /api/dossiers/:id/start-review | Phase 1 |  | To Do | Bat dau review
Sky-Lux-072 |  |  | API-WORKFLOW-003-POST-api-dossiers-id-request-changes | POST | /api/dossiers/:id/request-changes | Phase 1 |  | To Do | Yeu cau chinh sua
Sky-Lux-073 |  |  | API-WORKFLOW-004-POST-api-dossiers-id-resubmit | POST | /api/dossiers/:id/resubmit | Phase 1 |  | To Do | Submit lai
Sky-Lux-074 |  |  | API-WORKFLOW-005-POST-api-dossiers-id-approve | POST | /api/dossiers/:id/approve | Phase 1 |  | To Do | Phe duyet
Sky-Lux-075 |  |  | API-WORKFLOW-006-POST-api-dossiers-id-complete | POST | /api/dossiers/:id/complete | Phase 1 |  | To Do | Hoan tat
Sky-Lux-076 |  |  | API-WORKFLOW-007-POST-api-dossiers-id-lock | POST | /api/dossiers/:id/lock | Phase 1 |  | To Do | Khoa ho so
Sky-Lux-077 |  |  | API-WORKFLOW-008-GET-api-dossiers-id-workflow-history | GET | /api/dossiers/:id/workflow-history | Phase 1 |  | To Do | Lich su workflow
Sky-Lux-078 |  |  | API-WORKFLOW-009-GET-api-dossiers-id-approvals | GET | /api/dossiers/:id/approvals | Phase 1 |  | To Do | Danh sach approval
Sky-Lux-079 | Lap trinh Backend API (Documents & Communication) | API Documents (MOD-DOCUMENT) |  |  |  | Phase 1
Sky-Lux-080 |  |  | API-DOCUMENT-001-GET-api-dossiers-id-documents | GET | /api/dossiers/:id/documents | Phase 1 |  | To Do | Danh sach tai lieu cua ho so
Sky-Lux-081 |  |  | API-DOCUMENT-002-POST-api-dossiers-id-documents | POST | /api/dossiers/:id/documents | Phase 1 |  | To Do | Upload tai lieu cho ho so
Sky-Lux-082 |  |  | API-DOCUMENT-003-GET-api-documents-id | GET | /api/documents/:id | Phase 1 |  | To Do | Chi tiet tai lieu
Sky-Lux-083 |  |  | API-DOCUMENT-004-DELETE-api-documents-id | DELETE | /api/documents/:id | Phase 1 |  | To Do | Xoa tai lieu
Sky-Lux-084 |  |  | API-DOCUMENT-005-GET-api-documents-id-download-url | GET | /api/documents/:id/download-url | Phase 1 |  | To Do | Lay signed URL download
Sky-Lux-085 | Lap trinh Backend API (Documents & Communication) | API Comments (MOD-COMMENT) |  |  |  | Phase 1
Sky-Lux-086 |  |  | API-COMMENT-001-GET-api-dossiers-id-comments | GET | /api/dossiers/:id/comments | Phase 1 |  | To Do | Danh sach binh luan ho so
Sky-Lux-087 |  |  | API-COMMENT-002-POST-api-dossiers-id-comments | POST | /api/dossiers/:id/comments | Phase 1 |  | To Do | Tao binh luan ho so
Sky-Lux-088 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API KPI (MOD-KPI) |  |  |  | Phase 1
Sky-Lux-089 |  |  | API-KPI-001-GET-api-kpi-me | GET | /api/kpi/me | Phase 1 |  | To Do | KPI ca nhan Sales
Sky-Lux-090 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Dashboard (MOD-DASHBOARD) |  |  |  | Phase 1
Sky-Lux-091 |  |  | API-DASHBOARD-001-GET-api-dashboard-sales | GET | /api/dashboard/sales | Phase 1 |  | To Do | Dashboard Sales
Sky-Lux-092 |  |  | API-DASHBOARD-002-GET-api-dashboard-operator | GET | /api/dashboard/operator | Phase 1 |  | To Do | Dashboard Operator
Sky-Lux-093 |  |  | API-DASHBOARD-003-GET-api-dashboard-ceo | GET | /api/dashboard/ceo | Phase 1 |  | To Do | Dashboard CEO
Sky-Lux-094 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Audit Log (MOD-AUDIT) |  |  |  | Phase 1
Sky-Lux-095 |  |  | API-AUDIT-001-GET-api-audit-logs | GET | /api/audit-logs | Phase 1 |  | To Do | Danh sach audit log
Sky-Lux-096 |  |  | API-AUDIT-002-GET-api-audit-logs-id | GET | /api/audit-logs/:id | Phase 1 |  | To Do | Chi tiet audit log
Sky-Lux-097 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Health (MOD-HEALTH) |  |  |  | Phase 1
Sky-Lux-098 |  |  | API-HEALTH-001-GET-api-health | GET | /api/health | Phase 1 |  | To Do | Health check
Sky-Lux-099 | Phase 2 - API Tasks |  |  |  |  | Phase 2
Sky-Lux-100 | Lap trinh Backend API (Documents & Communication) | API Document Versions (MOD-DOCVER) |  |  |  | Phase 2
Sky-Lux-101 |  |  | API-DOCVER-001-GET-api-documents-id-versions | GET | /api/documents/:id/versions | Phase 2 |  | To Do | Danh sach version tai lieu
Sky-Lux-102 |  |  | API-DOCVER-002-POST-api-documents-id-versions | POST | /api/documents/:id/versions | Phase 2 |  | To Do | Tao version tai lieu
Sky-Lux-103 | Lap trinh Backend API (Documents & Communication) | API Conversations (MOD-CHAT) |  |  |  | Phase 2
Sky-Lux-104 |  |  | API-CHAT-001-GET-api-conversations | GET | /api/conversations | Phase 2 |  | To Do | Danh sach hoi thoai
Sky-Lux-105 |  |  | API-CHAT-002-POST-api-conversations | POST | /api/conversations | Phase 2 |  | To Do | Tao hoi thoai
Sky-Lux-106 |  |  | API-CHAT-003-GET-api-conversations-id | GET | /api/conversations/:id | Phase 2 |  | To Do | Chi tiet hoi thoai
Sky-Lux-107 |  |  | API-CHAT-004-GET-api-dossiers-dossierid-conversation | GET | /api/dossiers/:dossierId/conversation | Phase 2 |  | To Do | Hoi thoai gan voi ho so
Sky-Lux-108 | Lap trinh Backend API (Documents & Communication) | API Messages (MOD-MESSAGE) |  |  |  | Phase 2
Sky-Lux-109 |  |  | API-MESSAGE-001-GET-api-conversations-id-messages | GET | /api/conversations/:id/messages | Phase 2 |  | To Do | Danh sach tin nhan
Sky-Lux-110 |  |  | API-MESSAGE-002-POST-api-conversations-id-messages | POST | /api/conversations/:id/messages | Phase 2 |  | To Do | Gui tin nhan
Sky-Lux-111 |  |  | API-MESSAGE-003-DELETE-api-messages-messageid | DELETE | /api/messages/:messageId | Phase 2 |  | To Do | Xoa tin nhan
Sky-Lux-112 | Lap trinh Backend API (Documents & Communication) | API Chat Read / Participants (MOD-PARTICIPANT) |  |  |  | Phase 2
Sky-Lux-113 |  |  | API-PARTICIPANT-001-POST-api-conversations-id-read | POST | /api/conversations/:id/read | Phase 2 |  | To Do | Danh dau da doc
Sky-Lux-114 |  |  | API-PARTICIPANT-002-GET-api-conversations-id-participants | GET | /api/conversations/:id/participants | Phase 2 |  | To Do | Danh sach thanh vien
Sky-Lux-115 |  |  | API-PARTICIPANT-003-POST-api-conversations-id-participants | POST | /api/conversations/:id/participants | Phase 2 |  | To Do | Them thanh vien
Sky-Lux-116 |  |  | API-PARTICIPANT-004-DELETE-api-conversations-id-participants-userid | DELETE | /api/conversations/:id/participants/:userId | Phase 2 |  | To Do | Xoa thanh vien
Sky-Lux-117 | Lap trinh Backend API (Documents & Communication) | WebSocket Chat Events (MOD-WS-CHAT) |  |  |  | Phase 2
Sky-Lux-118 |  |  | API-WS-CHAT-001-WS-ws-chat-messagesend | WS | /ws/chat message:send | Phase 2 |  | To Do | Gui tin nhan realtime
Sky-Lux-119 |  |  | API-WS-CHAT-002-WS-ws-chat-messageread | WS | /ws/chat message:read | Phase 2 |  | To Do | Danh dau doc realtime
Sky-Lux-120 |  |  | API-WS-CHAT-003-WS-ws-chat-typingstart | WS | /ws/chat typing:start | Phase 2 |  | To Do | Bat trang thai dang go
Sky-Lux-121 |  |  | API-WS-CHAT-004-WS-ws-chat-typingstop | WS | /ws/chat typing:stop | Phase 2 |  | To Do | Tat trang thai dang go
Sky-Lux-122 |  |  | API-WS-CHAT-005-WS-ws-chat-messagereceived | WS | /ws/chat message:received | Phase 2 |  | To Do | Nhan tin nhan moi
Sky-Lux-123 |  |  | API-WS-CHAT-006-WS-ws-chat-messageread-updated | WS | /ws/chat message:read_updated | Phase 2 |  | To Do | Cap nhat trang thai doc
Sky-Lux-124 |  |  | API-WS-CHAT-007-WS-ws-chat-conversationupdated | WS | /ws/chat conversation:updated | Phase 2 |  | To Do | Cap nhat hoi thoai
Sky-Lux-125 |  |  | API-WS-CHAT-008-WS-ws-chat-notificationunread-count | WS | /ws/chat notification:unread_count | Phase 2 |  | To Do | Cap nhat so tin chua doc
Sky-Lux-126 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Tasks (MOD-TASK) |  |  |  | Phase 2
Sky-Lux-127 |  |  | API-TASK-001-GET-api-tasks | GET | /api/tasks | Phase 2 |  | To Do | Danh sach task
Sky-Lux-128 |  |  | API-TASK-002-GET-api-tasks-id | GET | /api/tasks/:id | Phase 2 |  | To Do | Chi tiet task
Sky-Lux-129 |  |  | API-TASK-003-POST-api-tasks | POST | /api/tasks | Phase 2 |  | To Do | Tao task
Sky-Lux-130 |  |  | API-TASK-004-PATCH-api-tasks-id | PATCH | /api/tasks/:id | Phase 2 |  | To Do | Cap nhat task
Sky-Lux-131 |  |  | API-TASK-005-DELETE-api-tasks-id | DELETE | /api/tasks/:id | Phase 2 |  | To Do | Xoa task
Sky-Lux-132 |  |  | API-TASK-006-POST-api-tasks-id-start | POST | /api/tasks/:id/start | Phase 2 |  | To Do | Bat dau task
Sky-Lux-133 |  |  | API-TASK-007-POST-api-tasks-id-complete | POST | /api/tasks/:id/complete | Phase 2 |  | To Do | Hoan thanh task
Sky-Lux-134 |  |  | API-TASK-008-POST-api-tasks-id-request-extension | POST | /api/tasks/:id/request-extension | Phase 2 |  | To Do | Yeu cau gia han
Sky-Lux-135 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Task Checklist (MOD-CHECKLIST) |  |  |  | Phase 2
Sky-Lux-136 |  |  | API-CHECKLIST-001-GET-api-tasks-id-checklist | GET | /api/tasks/:id/checklist | Phase 2 |  | To Do | Danh sach checklist
Sky-Lux-137 |  |  | API-CHECKLIST-002-POST-api-tasks-id-checklist | POST | /api/tasks/:id/checklist | Phase 2 |  | To Do | Tao checklist item
Sky-Lux-138 |  |  | API-CHECKLIST-003-PATCH-api-tasks-id-checklist-itemid | PATCH | /api/tasks/:id/checklist/:itemId | Phase 2 |  | To Do | Cap nhat checklist item
Sky-Lux-139 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Payments / Debt (MOD-PAYMENT) |  |  |  | Phase 2
Sky-Lux-140 |  |  | API-PAYMENT-001-GET-api-dossiers-id-payments | GET | /api/dossiers/:id/payments | Phase 2 |  | To Do | Danh sach thanh toan
Sky-Lux-141 |  |  | API-PAYMENT-002-POST-api-dossiers-id-payments | POST | /api/dossiers/:id/payments | Phase 2 |  | To Do | Tao thanh toan
Sky-Lux-142 |  |  | API-PAYMENT-003-GET-api-payments-id | GET | /api/payments/:id | Phase 2 |  | To Do | Chi tiet thanh toan
Sky-Lux-143 |  |  | API-PAYMENT-004-PATCH-api-payments-id | PATCH | /api/payments/:id | Phase 2 |  | To Do | Cap nhat thanh toan
Sky-Lux-144 |  |  | API-PAYMENT-005-GET-api-dossiers-id-finance-summary | GET | /api/dossiers/:id/finance-summary | Phase 2 |  | To Do | Tong hop tai chinh ho so
Sky-Lux-145 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API KPI (MOD-KPI) |  |  |  | Phase 2
Sky-Lux-146 |  |  | API-KPI-002-GET-api-kpis | GET | /api/kpis | Phase 2 |  | To Do | Danh sach KPI
Sky-Lux-147 |  |  | API-KPI-003-POST-api-kpis-targets | POST | /api/kpis/targets | Phase 2 |  | To Do | Tao target KPI
Sky-Lux-148 |  |  | API-KPI-004-PATCH-api-kpis-targets-id | PATCH | /api/kpis/targets/:id | Phase 2 |  | To Do | Cap nhat target KPI
Sky-Lux-149 |  |  | API-KPI-005-GET-api-kpis-sales | GET | /api/kpis/sales | Phase 2 |  | To Do | KPI Sales
Sky-Lux-150 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Reports (MOD-REPORT) |  |  |  | Phase 2
Sky-Lux-151 |  |  | API-REPORT-001-GET-api-reports-revenue | GET | /api/reports/revenue | Phase 2 |  | To Do | Bao cao doanh thu
Sky-Lux-152 |  |  | API-REPORT-002-GET-api-reports-sales-performance | GET | /api/reports/sales-performance | Phase 2 |  | To Do | Bao cao hieu suat Sales
Sky-Lux-153 |  |  | API-REPORT-003-GET-api-reports-customer | GET | /api/reports/customer | Phase 2 |  | To Do | Bao cao khach hang
Sky-Lux-154 |  |  | API-REPORT-004-GET-api-reports-supplier | GET | /api/reports/supplier | Phase 2 |  | To Do | Bao cao nha cung cap
Sky-Lux-155 |  |  | API-REPORT-005-POST-api-reports-export | POST | /api/reports/export | Phase 2 |  | To Do | Export bao cao
Sky-Lux-156 | Lap trinh Backend API (Tasks, Finance, KPI & Ops) | API Accounting Period (MOD-ACCOUNTING) |  |  |  | Phase 2
Sky-Lux-157 |  |  | API-ACCOUNTING-001-GET-api-accounting-periods | GET | /api/accounting-periods | Phase 2 |  | To Do | Danh sach ky ke toan
Sky-Lux-158 |  |  | API-ACCOUNTING-002-POST-api-accounting-periods | POST | /api/accounting-periods | Phase 2 |  | To Do | Tao ky ke toan
Sky-Lux-159 |  |  | API-ACCOUNTING-003-POST-api-accounting-periods-id-lock | POST | /api/accounting-periods/:id/lock | Phase 2 |  | To Do | Khoa ky ke toan
Sky-Lux-160 |  |  | API-ACCOUNTING-004-POST-api-accounting-periods-id-unlock | POST | /api/accounting-periods/:id/unlock | Phase 2 |  | To Do | Mo khoa ky ke toan
Sky-Lux-161 | Phase 3 - SaaS Platform API Tasks |  |  |  |  | Phase 3 |  |  | Trình tự đã sắp theo phụ thuộc nghiệp vụ; triển khai từ trên xuống.
Sky-Lux-162 | Lap trinh Backend API (SaaS Platform & Super Admin) | Organizations / Tenants (MOD-PLATFORM-ORG) |  |  |  | Phase 3
Sky-Lux-163 |  |  | API-SAAS-ORG-003-POST-api-platform-organizations | POST | /api/platform/organizations | Phase 3 |  | To Do | Tạo tenant mới
Sky-Lux-164 |  |  | API-SAAS-ORG-001-GET-api-platform-organizations | GET | /api/platform/organizations | Phase 3 |  | To Do | Liệt kê doanh nghiệp/tenant
Sky-Lux-165 |  |  | API-SAAS-ORG-002-GET-api-platform-organizations-organizationid | GET | /api/platform/organizations/:organizationId | Phase 3 |  | To Do | Xem chi tiết tenant
Sky-Lux-166 |  |  | API-SAAS-ORG-004-PATCH-api-platform-organizations-organizationid | PATCH | /api/platform/organizations/:organizationId | Phase 3 |  | To Do | Cập nhật hồ sơ tenant
Sky-Lux-167 |  |  | API-SAAS-ORG-005-POST-api-platform-organizations-organizationid-status | POST | /api/platform/organizations/:organizationId/status | Phase 3 |  | To Do | Đổi trạng thái tenant
Sky-Lux-168 |  |  | API-SAAS-ORG-006-POST-api-platform-organizations-organizationid-archive | POST | /api/platform/organizations/:organizationId/archive | Phase 3 |  | To Do | Archive tenant
Sky-Lux-169 | Lap trinh Backend API (SaaS Platform & Super Admin) | Service Plans / Entitlements (MOD-PLATFORM-PLAN) |  |  |  | Phase 3
Sky-Lux-170 |  |  | API-SAAS-PLAN-003-POST-api-platform-plans | POST | /api/platform/plans | Phase 3 |  | To Do | Tạo gói dịch vụ
Sky-Lux-171 |  |  | API-SAAS-PLAN-001-GET-api-platform-plans | GET | /api/platform/plans | Phase 3 |  | To Do | Danh sách gói dịch vụ
Sky-Lux-172 |  |  | API-SAAS-PLAN-002-GET-api-platform-plans-planid | GET | /api/platform/plans/:planId | Phase 3 |  | To Do | Chi tiết gói
Sky-Lux-173 |  |  | API-SAAS-PLAN-004-PATCH-api-platform-plans-planid | PATCH | /api/platform/plans/:planId | Phase 3 |  | To Do | Cập nhật gói
Sky-Lux-174 |  |  | API-SAAS-PLAN-005-POST-api-platform-plans-planid-archive | POST | /api/platform/plans/:planId/archive | Phase 3 |  | To Do | Ngừng cung cấp gói
Sky-Lux-175 | Lap trinh Backend API (SaaS Platform & Super Admin) | Subscriptions / Licenses (MOD-PLATFORM-SUBSCRIPTION) |  |  |  | Phase 3
Sky-Lux-176 |  |  | API-SAAS-SUB-003-POST-api-platform-subscriptions | POST | /api/platform/subscriptions | Phase 3 |  | To Do | Cấp thuê bao
Sky-Lux-177 |  |  | API-SAAS-SUB-001-GET-api-platform-subscriptions | GET | /api/platform/subscriptions | Phase 3 |  | To Do | Danh sách giấy phép/thuê bao
Sky-Lux-178 |  |  | API-SAAS-SUB-002-GET-api-platform-subscriptions-subscriptionid | GET | /api/platform/subscriptions/:subscriptionId | Phase 3 |  | To Do | Chi tiết thuê bao
Sky-Lux-179 |  |  | API-SAAS-SUB-004-POST-api-platform-subscriptions-subscriptionid-change-plan | POST | /api/platform/subscriptions/:subscriptionId/change-plan | Phase 3 |  | To Do | Nâng/hạ gói
Sky-Lux-180 |  |  | API-SAAS-SUB-005-POST-api-platform-subscriptions-subscriptionid-renew | POST | /api/platform/subscriptions/:subscriptionId/renew | Phase 3 |  | To Do | Gia hạn thuê bao
Sky-Lux-181 |  |  | API-SAAS-SUB-006-POST-api-platform-subscriptions-subscriptionid-suspend | POST | /api/platform/subscriptions/:subscriptionId/suspend | Phase 3 |  | To Do | Tạm ngưng giấy phép
Sky-Lux-182 |  |  | API-SAAS-SUB-007-POST-api-platform-subscriptions-subscriptionid-reactivate | POST | /api/platform/subscriptions/:subscriptionId/reactivate | Phase 3 |  | To Do | Mở lại giấy phép
Sky-Lux-183 |  |  | API-SAAS-SUB-008-POST-api-platform-subscriptions-subscriptionid-cancel | POST | /api/platform/subscriptions/:subscriptionId/cancel | Phase 3 |  | To Do | Hủy thuê bao
Sky-Lux-184 | Lap trinh Backend API (SaaS Platform & Super Admin) | Contracts / SaaS Billing (MOD-PLATFORM-BILLING) |  |  |  | Phase 3
Sky-Lux-185 |  |  | API-SAAS-BILL-002-POST-api-platform-contracts | POST | /api/platform/contracts | Phase 3 |  | To Do | Tạo hợp đồng
Sky-Lux-186 |  |  | API-SAAS-BILL-001-GET-api-platform-contracts | GET | /api/platform/contracts | Phase 3 |  | To Do | Danh sách hợp đồng
Sky-Lux-187 |  |  | API-SAAS-BILL-005-POST-api-platform-invoices | POST | /api/platform/invoices | Phase 3 |  | To Do | Phát hành hóa đơn
Sky-Lux-188 |  |  | API-SAAS-BILL-003-GET-api-platform-invoices | GET | /api/platform/invoices | Phase 3 |  | To Do | Danh sách hóa đơn SaaS
Sky-Lux-189 |  |  | API-SAAS-BILL-004-GET-api-platform-invoices-invoiceid | GET | /api/platform/invoices/:invoiceId | Phase 3 |  | To Do | Chi tiết hóa đơn SaaS
Sky-Lux-190 |  |  | API-SAAS-BILL-006-POST-api-platform-invoices-invoiceid-payments | POST | /api/platform/invoices/:invoiceId/payments | Phase 3 |  | To Do | Ghi nhận thanh toán
Sky-Lux-191 |  |  | API-SAAS-BILL-007-POST-api-platform-invoices-invoiceid-void | POST | /api/platform/invoices/:invoiceId/void | Phase 3 |  | To Do | Hủy hóa đơn
Sky-Lux-192 | Lap trinh Backend API (SaaS Platform & Super Admin) | Trial / Onboarding (MOD-PLATFORM-ONBOARDING) |  |  |  | Phase 3
Sky-Lux-193 |  |  | API-SAAS-ONBOARD-001-POST-api-platform-trials | POST | /api/platform/trials | Phase 3 |  | To Do | Khởi tạo dùng thử
Sky-Lux-194 |  |  | API-SAAS-ONBOARD-002-POST-api-platform-trials-trialid-extend | POST | /api/platform/trials/:trialId/extend | Phase 3 |  | To Do | Gia hạn dùng thử
Sky-Lux-195 |  |  | API-SAAS-ONBOARD-004-GET-api-platform-organizations-organizationid-onboarding | GET | /api/platform/organizations/:organizationId/onboarding | Phase 3 |  | To Do | Xem checklist onboarding
Sky-Lux-196 |  |  | API-SAAS-ONBOARD-005-PATCH-api-platform-organizations-organizationid-onboarding | PATCH | /api/platform/organizations/:organizationId/onboarding | Phase 3 |  | To Do | Cập nhật checklist onboarding
Sky-Lux-197 |  |  | API-SAAS-ONBOARD-003-POST-api-platform-trials-trialid-convert | POST | /api/platform/trials/:trialId/convert | Phase 3 |  | To Do | Chuyển trial thành thuê bao trả phí
Sky-Lux-198 | Lap trinh Backend API (SaaS Platform & Super Admin) | Support Desk (MOD-PLATFORM-SUPPORT) |  |  |  | Phase 3
Sky-Lux-199 |  |  | API-SAAS-SUPPORT-002-POST-api-support-tickets | POST | /api/support-tickets | Phase 3 |  | To Do | Tenant tạo yêu cầu hỗ trợ
Sky-Lux-200 |  |  | API-SAAS-SUPPORT-001-GET-api-platform-support-tickets | GET | /api/platform/support-tickets | Phase 3 |  | To Do | Danh sách yêu cầu hỗ trợ
Sky-Lux-201 |  |  | API-SAAS-SUPPORT-003-GET-api-platform-support-tickets-ticketid | GET | /api/platform/support-tickets/:ticketId | Phase 3 |  | To Do | Chi tiết yêu cầu hỗ trợ
Sky-Lux-202 |  |  | API-SAAS-SUPPORT-006-POST-api-platform-support-tickets-ticketid-assignee | POST | /api/platform/support-tickets/:ticketId/assignee | Phase 3 |  | To Do | Phân công ticket
Sky-Lux-203 |  |  | API-SAAS-SUPPORT-004-POST-api-platform-support-tickets-ticketid-replies | POST | /api/platform/support-tickets/:ticketId/replies | Phase 3 |  | To Do | Phản hồi yêu cầu hỗ trợ
Sky-Lux-204 |  |  | API-SAAS-SUPPORT-005-PATCH-api-platform-support-tickets-ticketid | PATCH | /api/platform/support-tickets/:ticketId | Phase 3 |  | To Do | Cập nhật trạng thái/ưu tiên ticket
Sky-Lux-205 | Lap trinh Backend API (SaaS Platform & Super Admin) | Platform Dashboard / Usage (MOD-PLATFORM-ANALYTICS) |  |  |  | Phase 3
Sky-Lux-206 |  |  | API-SAAS-DASH-001-GET-api-platform-dashboard | GET | /api/platform/dashboard | Phase 3 |  | To Do | Tổng quan vận hành nền tảng
Sky-Lux-207 |  |  | API-SAAS-DASH-002-GET-api-platform-usage | GET | /api/platform/usage | Phase 3 |  | To Do | Thống kê sử dụng theo tenant
Sky-Lux-208 | Lap trinh Backend API (SaaS Platform & Super Admin) | Product Releases (MOD-PLATFORM-RELEASE) |  |  |  | Phase 3
Sky-Lux-209 |  |  | API-SAAS-RELEASE-002-POST-api-platform-releases | POST | /api/platform/releases | Phase 3 |  | To Do | Tạo bản phát hành nháp
Sky-Lux-210 |  |  | API-SAAS-RELEASE-001-GET-api-platform-releases | GET | /api/platform/releases | Phase 3 |  | To Do | Danh sách phiên bản sản phẩm
Sky-Lux-211 |  |  | API-SAAS-RELEASE-003-PATCH-api-platform-releases-releaseid | PATCH | /api/platform/releases/:releaseId | Phase 3 |  | To Do | Cập nhật release draft
Sky-Lux-212 |  |  | API-SAAS-RELEASE-004-POST-api-platform-releases-releaseid-publish | POST | /api/platform/releases/:releaseId/publish | Phase 3 |  | To Do | Phát hành/cập nhật rollout
Sky-Lux-213 |  |  | API-SAAS-RELEASE-005-POST-api-platform-releases-releaseid-retire | POST | /api/platform/releases/:releaseId/retire | Phase 3 |  | To Do | Ngừng hỗ trợ phiên bản
Sky-Lux-214 | Lap trinh Backend API (SaaS Platform & Super Admin) | Privileged Support Access (MOD-PLATFORM-ACCESS) |  |  |  | Phase 3
Sky-Lux-215 |  |  | API-SAAS-ACCESS-001-POST-api-platform-organizations-organizationid-support-access-grants | POST | /api/platform/organizations/:organizationId/support-access-grants | Phase 3 |  | To Do | Cấp quyền hỗ trợ tạm thời
Sky-Lux-216 |  |  | API-SAAS-ACCESS-003-GET-api-platform-organizations-organizationid-support-access-grants | GET | /api/platform/organizations/:organizationId/support-access-grants | Phase 3 |  | To Do | Lịch sử quyền hỗ trợ tenant
Sky-Lux-217 |  |  | API-SAAS-ACCESS-004-GET-api-platform-support-access-grants-grantid | GET | /api/platform/support-access-grants/:grantId | Phase 3 |  | To Do | Chi tiết grant hỗ trợ
Sky-Lux-218 |  |  | API-SAAS-ACCESS-002-POST-api-platform-support-access-grants-grantid-revoke | POST | /api/platform/support-access-grants/:grantId/revoke | Phase 3 |  | To Do | Thu hồi quyền hỗ trợ

## Notes
Noi dung | Gia tri
Nguon | sky_lux_api_tasks.xlsx
Thay doi | Sap xep lai theo Phase 1 truoc, Phase 2 sau; khong con gia tri phase lai.
Quy tac tach phase | Suppliers va Workflow dua ve Phase 1; Chat/Task/Payment/Accounting/Document Version/Reports/KPI nang cao dua ve Phase 2.
Tong endpoint/event | 177
Phase 1 endpoint/event | 79
Phase 2 endpoint/event | 50
Quy tac ma task | Danh lai Sky-Lux-001... theo thu tu phase moi.
Phase 3 endpoint/event | 48